## Sheet1
Next:
	Installation instructions
	Issues from previous repos

	Osvcad – node transformations + transformation around self anchor

					Issue	Who	Estimate
pyosv
Taks list (this document)					GF	4h
Installation instructions					# 1	GF
Issues from previous repos					GF
Link issues to tasks					GF

party

File format
	Units management : list in units section of JSON					GF
	Nomenclature enforcement					GF		Option to strictly enforce a nomenclature defined in a template file (carried over to the final PJSON)
	'include' library creation mechanism + impact on the autocreation					GF
Templating
	Skeleton generation from name					GF
	Automate library.json generation based on the contents of the input file (contains {{ generators }}, aliases, __alias__					GF
Use
	STEP, STL and HTML generation should be possible (but not automatic)					GF
	Auto-computed geometric signature based on SVD (Singular Value Decomposition)					GF
Documentation
	Library documentation generation from the PJSON file					GF		Generating one .rst per PJSON library file
	Sphinx documentation of **party**, of the PJSON file format and of the template format					GF
	Technical drawings integration					GF
	Read-the-docs					GF
Tests and checks
	function to test the generated scripts are ok					GF
	Metadata is the same for each part (the list of fields is also returned)					GF
	Check units are coherent (every field linked to a unit)					GF
	Checks for duplicate part ids					GF
Examples
	Improve screw geometry generator					GF
UI
	Desktop PJSON library browsing/searching UI					GF
	Web PJSON library browsing/searching UI					GF

ccad
	Cleanup from unused parts (philosophy : ccad is a PythonOCC wrapper)					GF
	Enhance the options to various routines to more encompass OCC's capabilities					GF
	Add edge intersection					GF
	Separate compound, compsolid from solid.					GF
	Transform ccad shape with a 4x3 matrix					GF

standard-cad-parts
Documentation
	Some SVG drawings for some ISO standards					GF	3d	ISO 4032, ISO 4014 and ISO 4762
Content
	Sample libraries					GF
	Create new libraries					Community

osvcad
General
	Nodes geometrical transformation functions (shape and anchors must move together)					GF
	Rotation and translation around self anchors					GF
	Assemblies management					GF
	Positionning with anchors fails in some cases					# 1	GF
Tests
	setup.py test					GF

Examples
	Random cubes organizing themselves using anchors					GF
	Visual testing of many configurations					GF
	Car modelling with graph					GF
Packaging
	setup.py					GF
UI

<Reverse-engineering> - name to be determined.

Code organisation
	Create separate repo for reverse engineering	?					BU

					GF